## 1
Please ensure this tracking sheet is completed as a group, as it will be used to monitor your individual participation within the team.
Team Members | Role/ Responsibilty | Email
Fabrice Mbarushimana | Team lead: project setup, discrete worked calculations, compiling the draft | f.mbarushim@alustudent.com
Teta Butera Nelly | Discrete distributions theory, continuous worked calculations, team review | t.nelly@alustudent.com
Elie Kuradusenge | Continuous distributions theory, code and plots, final submission check and tracker | e.kuradusen@alustudent.com
Task Allocation and Tracker
| Task Allocated | Assigned Member | Deadline | Completion Status (Not Started/In Progress/Completed/Did not participate) | Reviewed by Team? (Yes/No) | Comments
| Read the brief, split the questions, set up the shared folder/notebook | Fabrice Mbarushimana | Fri 23 Oct 2026 | Completed | Yes | Work started here; questions split across the three members.
| Discrete distributions (Binomial/Poisson): theory and formulas | Teta Butera Nelly | Fri 23 Oct 2026 | Completed | Yes
| Continuous distributions (Normal/Exponential): theory and formulas | Elie Kuradusenge | Fri 23 Oct 2026 | Completed | Yes
| Worked calculations for the discrete distributions | Fabrice Mbarushimana | Sat 24 Oct 2026 | Completed | Yes
| Worked calculations for the continuous distributions | Teta Butera Nelly | Sat 24 Oct 2026 | Completed | Yes
| Code/simulation and plots (histograms, PMF/PDF curves) | Elie Kuradusenge | Sat 24 Oct 2026 | Completed | Yes
| Compile everything into one draft | Fabrice Mbarushimana | Sun 25 Oct 2026 | Completed | Yes | Single draft shared with the team.
| Team review: check answers, proofread, fix gaps | Teta Butera Nelly | Sun 25 Oct 2026 | Completed | Yes | Corrections sent back to the owners.
| Final submission check, plus complete the tracker and meeting log | Elie Kuradusenge | Mon 26 Oct 2026 | In progress | No | Final deadline is today.
Meeting Attendance Log
Meeting Date | Agenda | Facilitator | Attendees | Key Discussion Points | Next Steps
Fri 23 Oct 2026 | Kick-off: read the brief and allocate tasks | Fabrice Mbarushimana | Fabrice Mbarushimana, Teta Butera Nelly, Elie Kuradusenge | Went through the brief, split the questions, agreed task owners and daily deadlines. | Theory sections (discrete and continuous) due the same day; set up the shared folder.
Sat 24 Oct 2026 | Progress check on theory and calculations | Teta Butera Nelly | Fabrice Mbarushimana, Teta Butera Nelly, Elie Kuradusenge | Reviewed the theory sections; agreed formulas and notation to use in the calculations. | Finish worked calculations and the code/plots today.
Sun 25 Oct 2026 | Review of the compiled draft | Teta Butera Nelly | Fabrice Mbarushimana, Teta Butera Nelly, Elie Kuradusenge | Checked answers, proofread, listed gaps and fixes. | Apply fixes; prepare final submission.
Mon 26 Oct 2026 | Final check before submission | Elie Kuradusenge | Fabrice Mbarushimana, Teta Butera Nelly, Elie Kuradusenge | Confirmed the final draft, tracker and meeting log are complete. | Submit the assignment.